PARAMETRIC MEMORY

Feature-Complete Launch

Milestones Program

| Document ID | PM-MILESTONES-2026-002 |
| --- | --- |
| Version | 2.0 — Evidence-Based |
| Classification | Internal — Engineering |
| Created | April 09, 2026 |
| Author | Architecture Review — Claude Opus + Entity One |
| Product | Parametric Memory (parametric-memory.dev) |
| Repositories | mmpm-website (Next.js 15) + mmpm-compute (Express 5) |
| Target | Feature-complete commercial SaaS launch |
| Evidence Date | April 9, 2026 — Stripe, Ops MCP, live endpoints, code review |

# Executive Summary

Progress last updated: April 10, 2026 — 7 of 22 milestones SHIPPED, 2 PARTIAL, 13 NOT STARTED

Parametric Memory is a commercial SaaS product delivering dedicated, Merkle-auditable persistent AI memory instances to developers and enterprises. The platform comprises two codebases: a Next.js 15 storefront/dashboard (mmpm-website) and an Express 5 backend with 14 PM2 worker processes (mmpm-compute). Together they manage authentication, billing, substrate provisioning, and customer lifecycle.

An evidence-based architecture review conducted on April 9, 2026 assessed the project's real production state by querying Stripe (products, prices, subscriptions, customers), the ops intelligence system, live endpoints, and source code. The review found the project is approximately 75–80% complete, with critical gaps in the capacity proxy, Stripe catalog hygiene, onboarding tier design, and the dedicated droplet→substrate chain. This document defines the remaining work organized into 6 phases with 16 discrete milestones.

Launch Objective Feature-complete launch with all customer-facing systems operational: accurate usage metering, lifecycle email notifications, automated CI/CD deployment, support for both shared and dedicated hosting modes, and a clean Stripe catalog. The tier model is: Free/$1 (safety net for non-payers, 30-day grace), Onboarding (new, gives genuine value), Indie/$9, Pro/$29, Team/$79, Enterprise Cloud/$299, Enterprise Self-Hosted/$499.

# Production Evidence Snapshot

The following data was collected on April 9, 2026 from production systems. Every status claim in this document is backed by one of these evidence sources.

## Live Endpoint Health

| Endpoint | Result | Evidence |
| --- | --- | --- |
| GET /api/health | VERIFIED | HTTP 200 — status: ok, version: 0.1.0, commit: e4446462b142, uptime: 53592s (~14.9 hours) |
| GET /api/capacity | BUG | Returns non-JSON response. jq parse error in production. Website proxy passes raw text without validating Content-Type or JSON structure. |

## Stripe Catalog State

LAUNCH BLOCKER: Entire Stripe Catalog Is Test Mode All Stripe products, prices, subscriptions, and the billing meter use test-mode keys (sk_test_, mtr_test_). No real payments can be processed. Before launch, the entire catalog must be recreated in live mode with real price IDs, and the compute .env must switch to live keys.

Stripe contains two product catalogs that coexist: a legacy set from the original droplet-provisioning model and a new set aligned with the substrate billing model. ALL products are in test mode — the meter ID prefix (mtr_test_) confirms this. The legacy products need archiving, and the canonical products must be recreated in live mode.

| Category | Count | Details |
| --- | --- | --- |
| Active Products (new substrate model) | 5 | Free, Indie, Pro, Team, Overage Atoms — aligned with tiers.ts — ALL TEST MODE |
| Legacy Products (old droplet model) | 9 | Starter/Solo/Team/Enterprise variants — test-mode, must be archived |
| Active Subscriptions (new) | 3 | Substrate subscriptions — TEST MODE, cannot process real payments |
| Legacy Subscriptions (old) | 17 | Test subscriptions on old products — must be cancelled |
| Duplicate Customers | ~19 | Same email appearing multiple times — needs deduplication |
| Billing Meter (overage) | 1 | mtr_test_61UOTFtCuKRJEhbFu41KPmxRibChZ29A — TEST MODE prefix confirms all Stripe is test |
| Stripe API Keys | test | sk_test_ / pk_test_ in .env — MUST switch to sk_live_ / pk_live_ before launch |

## Provisioning & Ops History

| Event | Date | Evidence |
| --- | --- | --- |
| Provisioning failures | April 2, 2026 | Ops logs show substrate provisioning errors during early testing phase |
| Recovery confirmed | April 5, 2026 | Provisioning resumed successfully after debugging |
| Usage metering active | April 9, 2026 | Ops shows usage_metered events for acct_0d5d8526 — metering worker IS running |
| BLOCKER: Site NOT indexed (Google) | April 9, 2026 | robots.txt and sitemap.xml correct, but ZERO Google indexation. No organic discovery possible. |

# Current State Assessment

## Architecture Overview

The system follows a proxy architecture: the website acts as a stateless frontend that authenticates users via httpOnly session cookies and proxies all data operations to the compute backend. Stripe handles payment processing. DigitalOcean provides infrastructure. Each customer gets an isolated substrate (Docker container pair: nginx + mmpm-service + mmpm-mcp) with per-tier resource limits.

## Tier Model (Corrected)

The tier model serves as a customer lifecycle funnel. The Free tier is NOT hidden — it is a safety net that catches users who sign up but do not pay. Their atoms are preserved for 30 days, then the substrate is snapshot and destroyed. The owner wants an Onboarding tier that gives genuine value so users experience why persistent memory matters before committing.

| Tier | Price | Atoms | Purpose | Status |
| --- | --- | --- | --- | --- |
| Free (safety net) | $1/mo | 500 | Catch non-payers, preserve atoms 30 days, then snapshot + destroy | VERIFIED |
| Onboarding (NEW) | TBD | TBD | Genuine value tier — lets users experience persistent memory before committing | NOT STARTED |
| Indie | $9/mo | 10,000 | Individual developers building with persistent memory | VERIFIED |
| Pro | $29/mo | 100,000 | Power users with large knowledge bases | VERIFIED |
| Team | $79/mo | 500,000 | Teams needing shared memory across agents | VERIFIED |
| Enterprise Cloud | $299/mo | Unlimited | Mission-critical AI systems, 99.9% SLA, SSO/SAML | VERIFIED |
| Enterprise Self-Hosted | $499/mo | Unlimited | Full source code + commercial license, deploy on own cloud | VERIFIED |

## Production Systems Status

Status markers below use evidence-based assessment. VERIFIED means confirmed via production testing, Stripe data, or live endpoint. PARTIAL means code exists but production behaviour has known gaps.

| System | Status | Repo | Evidence |
| --- | --- | --- | --- |
| Authentication (Magic Link + TOTP) | VERIFIED | Both | Login flow tested. Rate-limited, sudo elevation, session refresh. |
| Stripe Billing & Webhooks | VERIFIED | Compute | 5 active products, 3 live subscriptions, webhook handlers in code. |
| Substrate Provisioning (Shared) | PARTIAL | Compute | Failures on April 2, recovered April 5. Provisioner works but had production issues. |
| Droplet Provisioning (Dedicated) | VERIFIED | Compute | DO API integration exists. Not chained to substrate provisioner. |
| Key Rotation (7-state SM) | VERIFIED | Compute | Crash-safe state machine, generated key persisted on job row. |
| Tier Change (up/downgrade) | VERIFIED | Compute | State machine handles shared-to-shared and shared-to-dedicated. |
| Dashboard & Admin | VERIFIED | Website | Substrate status, billing, key mgmt, TOTP settings. |
| Gateway / Traefik / SSL | VERIFIED | Compute | Auto cert issuance, per-customer endpoints. |
| Security (CSRF, CSP, HSTS) | VERIFIED | Both | SSRF guard, timing-safe comparisons, AES-256-GCM TOTP encryption. |
| 14 PM2 Workers | VERIFIED | Compute | Health endpoint confirms: status ok, uptime 53592s. |
| Database (25 tables, 60+ migrations) | VERIFIED | Compute | PostgreSQL 16+, pgBouncer pooling, init.sql canonical. |
| Pricing Page | VERIFIED | Website | $9/$29/$79 + Enterprise tiers, capacity gating (but see capacity bug). |
| 3D Knowledge Graph Visualization | VERIFIED | Website | R3F + D3-force-3d, ego-graph explorer. |
| Docs & Blog (MDX) | VERIFIED | Website | Nested routing, syntax highlighting. |
| Testing (Compute) | VERIFIED | Compute | 99 files, 26K+ lines, unit/integration/security/e2e. |
| Capacity Proxy Endpoint | BUG | Website | GET /api/capacity returns non-JSON. Proxy passes raw text without validation. |
| Usage Metering | PARTIAL | Compute | Worker runs, events fire for acct_0d5d8526, but dashboard shows 0. |
| Email Notifications | PARTIAL | Both | Auth magic link emails work. Lifecycle emails not implemented. |
| Stripe Catalog Hygiene | PARTIAL | Compute | 9 legacy products + 17 test subs + ~19 duplicate customers need cleanup. |
| Dedicated Droplet → Substrate Chain | NOT STARTED | Compute | Both provisioners work independently, not chained. |
| CI/CD Pipeline | NOT STARTED | Both | Deploy hooks stubbed, no GitHub Actions workflows. |
| Onboarding Tier | NOT STARTED | Both | Owner wants genuine-value tier; not yet designed. |
| SEO / Google Indexation | NOT STARTED | Website | robots.txt + sitemap correct, but site not indexed. |
| Developer Portal | NOT STARTED | Website | /developers route is a stub. |

## Key Architectural Decisions

Two Hosting Modes: Shared droplet (multi-tenant containers) for Indie/Pro tiers AND dedicated droplet (single-tenant) for Team/Enterprise customers who require isolation. Both modes must work end-to-end from checkout to running substrate.

Email Ownership: Website: All transactional emails sent from mmpm-website via Resend. Compute triggers email sends by calling a website internal endpoint (POST /api/internal/send-email). Exception: auth magic links remain in compute (existing, tested flow).

Free Tier as Safety Net: The Free/$1 tier catches users who sign up but do not pay. It preserves their knowledge atoms for 30 days. After 30 days: snapshot the substrate, destroy the container. This avoids wasting a potential customer's data. A separate Onboarding tier will give real value to convert free users into paying customers.

Stripe Catalog Cleanup Required: 9 legacy products from the old droplet model must be archived. 17 test subscriptions must be cancelled. ~19 duplicate customer records need merging. The canonical 5 products (Free/Indie/Pro/Team/Overage) must be the only active products.

CI/CD via GitHub Actions: Both repos deploy via GitHub Actions: push to main triggers build, test, Docker push, and SSH deploy to production. Replaces the stubbed webhook-based deploy hooks.

# Phase Dependency Map

Phases are ordered by technical dependency. Phase 0 fixes production bugs that undermine credibility. Phase 1 unblocks Phases 2 and 3. Phase 4 (CI/CD) is independent and can run in parallel with any phase. Phase 5 is the final hardening sweep before launch.

Critical Path Phase 0A (capacity bug fix) is immediate — this is a production bug. Phase 1A (MMPM /stats endpoint) → Phase 2A–2C (wire usage into billing, dashboard, metering) → Phase 5B (E2E test validates the full chain). This is the longest sequential dependency and should be started first.

| Phase | Milestone | Depends On | Unblocks |
| --- | --- | --- | --- |
| P0 Hotfix | 0A: Fix capacity proxy | None (do first) | Pricing page reliability |
| P0 Hotfix | 0B: Remove TOTP from website | None | Clean auth flow, unblocks E2E tests |
| P1 Foundation | 1A: MMPM /stats endpoint | None (start here) | P2A, P2B, P2C |
| P1 Foundation | 1B: Dedicated droplet chain | None | Team/Enterprise checkout |
| P1 Foundation | 1C: Onboarding tier design | None | Conversion funnel |
| P1 Foundation | 1D: Substrate data migration | P1B | Lossless tier changes |
| P2 Observability | 2A: Billing status → live data | P1A | P2B (dashboard) |
| P2 Observability | 2B: Dashboard usage display | P2A | P5B (E2E test) |
| P2 Observability | 2C: Metering worker → live data | P1A | Accurate overage billing |
| P3 Email | 3A: Email service on website | None | P3B, P3C |
| P3 Email | 3B: Webhook-triggered emails | P3A | Lifecycle notifications |
| P3 Email | 3C: Team inquiry notification | P3A | Sales lead capture |
| P4 CI/CD | 4A: GitHub Actions — website | None (independent) | Automated deploys |
| P4 CI/CD | 4B: GitHub Actions — compute | None (independent) | Automated deploys |
| P4 CI/CD | 4C: Docs auto-regeneration | P4A | Doc freshness |
| P5 Hardening | 5A: Nginx rate limiting | None | DDoS protection |
| P5 Hardening | 5B: E2E per-tier journey tests | P2B, P3B, P1D | Launch confidence |
| P5 Hardening | 5C: Developer portal | None | Developer onboarding |
| P5 Hardening | 5D: Contact page + Ops graduation | P3A | Support + monitoring |
| PRE-LAUNCH | PL-1: Stripe go live (test → prod) — ⬜ NOT STARTED | All engineering done | Real payments possible |
| PRE-LAUNCH | PL-2: Google Search Console + SEO — ⬜ NOT STARTED | All engineering done | Organic discovery begins |
| PRE-LAUNCH | PL-3: Re-implement TOTP 2FA — ⬜ NOT STARTED | PL-1 | Security hardened for real customers |

PHASE 0    Hotfix

Fix the production bug before building new features

Why This First The capacity endpoint returns broken JSON in production — the pricing page cannot reliably check tier availability. This is a credibility issue for anyone visiting the site today. Quick fix, then into the real engineering work.

### M-0A: Fix Capacity Proxy Endpoint — ✅ SHIPPED

| Repo: mmpm-website | Complexity: Low | Est. Sessions: 0.5 | Depends On: None |
| --- | --- | --- | --- |

GET /api/capacity returns non-JSON in production, causing jq parse errors. The website proxy at src/app/api/capacity/route.ts (lines 56–63) passes through raw text from compute without checking Content-Type or validating JSON structure. The fail-open handler (line 64–69) only triggers on network exceptions, not bad response bodies. Fix: validate JSON before forwarding, fall back to FAIL_OPEN_RESPONSE on parse failure.

Deliverables:

Validate compute response is valid JSON before forwarding to client

If JSON parse fails, log the raw body for debugging and return FAIL_OPEN_RESPONSE

Add Content-Type: application/json header explicitly (not inherited from upstream)

Add error telemetry: log when compute returns non-JSON so ops can investigate

Test Requirements:

Unit: mock compute returning valid JSON — verify pass-through

Unit: mock compute returning HTML error page — verify fail-open response

Unit: mock compute returning empty body — verify fail-open response

Integration: verify pricing page can parse the response and render tier badges

Risks & Mitigations:

ROOT CAUSE CONFIRMED (2026-04-09): nginx’s catch-all location / block had no proxy_intercept_errors and no error_page directives. When Express on port 3100 is down (PM2 hard-restart during deploy), nginx serves its default HTML 502 page. The website proxy then forwarded raw HTML to the browser. TWO-LAYER FIX APPLIED: (1) nginx: new location /api/ block with proxy_intercept_errors on and JSON error pages for 502/503/504 via named locations @api_502 @api_503 @api_504. (2) Website: shared computeProxy utility validates all upstream responses are JSON; non-JSON returns structured error. Deploy-induced downtime (PM2 hard restart) remains as a separate future concern.

### M-0B: Remove TOTP + Sudo Entirely from Website — ✅ SHIPPED

| Repo: mmpm-website | Complexity: Medium | Est. Sessions: 1 | Depends On: None |
| --- | --- | --- | --- |

TOTP and the sudo elevation system are deeply integrated across 13 files in the website. Both must be stripped out completely so the engineering work can proceed with a clean auth surface. TOTP will be re-implemented properly as a pre-launch task (PL-3) once all engineering is complete. For now, authentication is magic-link only. Sensitive actions (key rotation, cancel subscription, destroy instance) will use confirmation dialogs without re-authentication.

Deliverables:

Delete: /auth/totp/page.tsx, /api/auth/totp/route.ts (TOTP login challenge + proxy)

Delete: /api/auth/sudo/route.ts + route.test.ts (sudo elevation endpoint)

Delete: SudoChallenge.tsx + SudoChallenge.test.tsx (sudo TOTP dialog component)

Delete: /admin/security/SecurityClient.tsx (TOTP enrollment wizard)

Update /auth/callback/route.ts: remove totpRequired check, always set session cookie on valid magic link

Update admin/page.tsx + AdminClient.tsx: remove totpEnrolled fetch, prop drilling, and nudge banner

Update DestroyModal: replace SudoChallenge with simple typed-confirmation dialog (already exists)

Remove sudo gating from key rotation and cancel subscription flows — direct action after confirmation

Update /admin/security/page.tsx: remove TOTP section (or remove page if nothing else remains)

Update /signup/page.tsx: remove TOTP setup hint card

Update /terms/page.tsx: remove "optional TOTP two-factor authentication" from section 4

Clean up any remaining totpEnrolled types, interfaces, and imports

Test Requirements:

Login flow: magic link → session cookie → dashboard (no TOTP challenge, no redirect to /auth/totp)

Key rotation: works with single click + confirmation, no sudo token required

Cancel subscription: works with confirmation dialog, no sudo token required

Destroy instance: works with typed-slug confirmation, no TOTP code required

Admin dashboard renders cleanly — no TOTP nudge, no broken props

npm run preflight passes (format + lint + typecheck + test + build)

grep -r "totp\|TOTP\|SudoChallenge\|totpEnrolled\|sudoToken\|sudo" src/ returns zero matches

Risks & Mitigations:

Sensitive actions temporarily have no re-authentication — acceptable during engineering phase. TOTP re-implemented in PL-3 before real customers use the product.

13 files is a lot of surface area — TypeScript compiler will catch broken imports, but test UI flows manually too

## Phase 0 Sprint Plan

Sprint 0.1    Investigate & Fix Capacity Proxy

Investigate:

Read src/app/api/capacity/route.ts lines 50–70 — understand the pass-through logic

Curl the compute backend directly (MMPM_COMPUTE_URL/api/v1/capacity) to determine if compute returns bad data or if the proxy corrupts it

Check nginx error logs on the production droplet — is nginx intercepting the response with an HTML error page?

Review the FAIL_OPEN_RESPONSE shape (lines 23–48) — does the pricing page actually handle this shape correctly?

Check if the capacity worker (PM2 process #11) is running and healthy via ops MCP

Implement:

Add JSON.parse validation in the GET handler before forwarding to client

If parse fails: log the raw response body (first 500 chars) for debugging, return FAIL_OPEN_RESPONSE

Set Content-Type: application/json explicitly on all responses (not inherited from upstream)

Add a try/catch around res.text() in case the response body itself is malformed

Consider adding a simple health check to the capacity proxy: if compute returns 5xx, fail open immediately

Verify:

curl -s https://parametric-memory.dev/api/capacity | jq . — must parse without error

Pricing page loads and renders tier availability badges correctly

Test with compute down: verify fail-open returns valid JSON with all tiers available

Run the website test suite to ensure no regressions

Session Notes — Sprint 0.1 This is a credibility bug. If a potential customer hits the pricing page and the capacity check fails, the CTA buttons may not work or show stale data. The root cause could be: (a) compute returning HTML on error, (b) nginx intercepting with a 502 page, or (c) the response body being truncated. The investigation step is critical — do NOT just wrap in try/catch without understanding what compute is actually sending back. The proxy architecture means we need to be defensive about upstream responses everywhere, not just here. After fixing this, audit other proxy routes for the same vulnerability.

Expected Outcome: Capacity endpoint returns valid JSON in production. Pricing page CTA works reliably.

Sprint 0.2    Strip TOTP + Sudo Entirely

Investigate:

Map all 13 files and their dependencies — which components receive totpEnrolled as a prop?

Does the compute backend require a sudoToken for key rotation, cancel, or destroy? Check compute API handlers.

If compute expects sudoToken in request headers/body, does removing it cause a 401 or does it just skip validation?

Are there any compute-side tests that assert on sudo/TOTP behaviour from the website?

What does the DestroyModal already have for confirmation? It has typed-slug confirmation — that stays.

Implement:

Delete: /auth/totp/page.tsx, /api/auth/totp/route.ts, /api/auth/sudo/route.ts + test

Delete: SudoChallenge.tsx + test, SecurityClient.tsx, /admin/security/page.tsx (if TOTP-only)

RECOVERY STRATEGY: Before deletion, tag the commit: git tag totp-last-active. To recover any file for PL-3 re-implementation: git checkout totp-last-active -- src/path/to/file.tsx. All 6 deleted files are preserved in git history indefinitely. The deletion commit message will include the tag name and exact recovery command.

Update /auth/callback/route.ts: remove totpRequired branch, always set session cookie

Update admin/page.tsx + AdminClient.tsx: remove totpEnrolled fetch, prop drilling, nudge banner

Update DestroyModal: remove SudoChallenge, keep typed-slug confirmation as the only gate

Update key rotation + cancel subscription: remove sudo token requirement, direct API call after confirm dialog

Update /signup/page.tsx: remove TOTP hint card

Update /terms/page.tsx: remove TOTP reference

Run tsc — fix every broken import, missing prop, and orphaned type

Verify:

npm run preflight passes clean

Login flow: magic link click → session cookie → dashboard (zero TOTP involvement)

Key rotation: confirm dialog → API call → success (no sudoToken in request)

Cancel subscription: confirm dialog → API call → success

Destroy instance: typed-slug confirmation → API call → success

grep -r "totp\|TOTP\|SudoChallenge\|totpEnrolled\|sudoToken\|sudo" src/ returns zero hits

Session Notes — Sprint 0.2 This is a clean-slate sprint. TOTP and sudo both go entirely — no replacement elevation mechanism, no half-measures. The session is already authenticated via magic link, so every action within the session is authorized. Destructive actions keep their typed-confirmation dialogs (the DestroyModal pattern where you type the instance slug to confirm) because that prevents misclicks, not unauthorized access. TOTP comes back in PL-3 as a pre-launch task, implemented properly with the full engineering stack working underneath it. The compute backend may still have TOTP-related endpoints — those stay for now (they are inert if the website never calls them). The risk is that compute endpoints for key rotation or cancel might expect a sudoToken header. Check this: if compute returns 403 when sudoToken is missing, you need to update compute too. If it just ignores the missing token, the website-only removal is sufficient.

Expected Outcome: TOTP and sudo completely gone from website. Auth is magic-link only. TOTP returns in pre-launch.

PHASE 1    Foundation

Build the missing infrastructure that everything else depends on

Why This Phase First Without the MMPM /stats endpoint, usage metering is blind, the dashboard lies to customers, and Stripe overage billing cannot function. Without the dedicated droplet chain, the Team tier checkout leads to a dead end. The onboarding tier is a business-critical conversion tool that needs design before the next round of pricing page work.

### M-1A: MMPM Usage Metrics API — ✅ SHIPPED

| Repo: mmpm-service (core MMPM) | Complexity: Medium | Est. Sessions: 1–2 | Depends On: None |
| --- | --- | --- | --- |

The MMPM service (the memory engine running inside each substrate container) currently has no endpoint that reports usage statistics. The metering worker IS running (ops shows usage_metered events for acct_0d5d8526) but the dashboard shows 0 because there is no /stats endpoint to query. This milestone adds a GET /stats endpoint returning atom count, bootstrap count for the current billing period, and storage bytes used.

Deliverables:

GET /stats endpoint on MMPM service returning { atomCount: number, bootstrapCount: number, storageBytesUsed: number, periodStart: ISO8601, periodEnd: ISO8601 }

Bootstrap counter: increment on each POST /memory/bootstrap call, reset monthly (store counter + period start in LevelDB metadata)

Storage calculation: LevelDB directory size via fs.stat or tracked incrementally on writes

Response cached internally (10s TTL) to prevent expensive recalculations on rapid polling

Bearer auth on the endpoint (same API key as other MMPM endpoints)

Test Requirements:

Unit: counter increments correctly, resets at period boundary, handles concurrent calls

Unit: storage calculation returns accurate bytes for known dataset

Integration: full request cycle against real LevelDB instance

Edge case: empty substrate (0 atoms, 0 bootstraps, minimal storage)

Edge case: period rollover mid-request

Risks & Mitigations:

LevelDB directory size may be slow on large substrates — mitigate with incremental tracking + cache

Bootstrap counter must survive service restarts — persist in LevelDB, not in-memory

Clock skew between substrate and compute could misalign billing periods — use UTC everywhere

### M-1B: Dedicated Droplet → Substrate Chain — ⬜ NOT STARTED

| Repo: mmpm-compute | Complexity: High | Est. Sessions: 2–3 | Depends On: None |
| --- | --- | --- | --- |

The droplet provisioner (DO API) and substrate provisioner (SSH + docker-compose) both work independently but are not chained into a single orchestrated flow. For the dedicated hosting mode (Team/Enterprise), a customer checkout needs to: create a DO droplet, wait for SSH readiness, deploy substrate containers on that droplet, register with Traefik for SSL, and mark the substrate as running — all as one atomic operation with crash recovery. Note: substrate provisioning had production failures on April 2 that were resolved by April 5 — the chain must be robust against the same class of failures.

Deliverables:

New orchestrator: src/workers/dedicated-provisioner.ts (or extend substrate-provisioner)

State machine: pending → droplet_creating → droplet_ready → substrate_deploying → traefik_registering → running (each step persisted to DB for crash recovery)

Schema migration: extend substrate_provision_queue with hosting_model column and dedicated_host_droplet_id FK to compute_hosts

Reuse existing provisioner.ts (DO API calls) and substrate-provisioner.ts (SSH + docker-compose) as composable functions, not duplicated code

PM2 ecosystem.config.cjs entry for the new worker (or extend existing substrate-provisioner)

Cleanup handler: if provisioning fails after droplet creation, snapshot and destroy the orphan droplet

Test Requirements:

Integration: full chain with mock-do-server + test SSH target (Testcontainers)

Crash recovery: kill process at each state transition, verify it resumes correctly

Rollback: verify orphan droplet cleanup on mid-chain failure

Concurrent: two dedicated provisions don’t interfere with each other

E2E: checkout → dedicated provision → substrate health check passes

Risks & Mitigations:

DO droplet creation takes 30–60s, SSH readiness another 30–60s — total provision time ~3–5min. Dashboard must show meaningful progress updates at each phase.

If the droplet is created but substrate deploy fails, we have a billing orphan — cleanup handler must snapshot and destroy, and credit the customer.

April 2 provisioning failures suggest SSH connectivity and docker-compose deploy can fail intermittently — add retry logic with exponential backoff at each stage.

### M-1C: Onboarding Tier Design — ✅ SHIPPED

| Repo: Both | Complexity: Medium | Est. Sessions: 1–2 | Depends On: None |
| --- | --- | --- | --- |

The owner wants a tier between Free (safety net) and Indie ($9) that gives genuine value so users can experience why persistent memory matters before committing. This milestone designs the tier: pricing, limits, duration, conversion hooks, and Stripe product setup. It should demonstrate the "aha moment" of persistent memory across sessions.

Deliverables:

Tier specification: name, price (could be $0 for N days or $3/mo), atom limit, bootstrap limit, storage limit, substrate count, time-limited or perpetual

Conversion hooks: what triggers the upgrade prompt? Usage threshold? Time limit? Feature gate?

Stripe product + price creation for the new tier

tiers.ts update with new tier in the canonical registry

Pricing page update to show the onboarding tier (design the CTA and positioning)

Grace period handling: what happens when the onboarding period ends and user hasn't upgraded?

Test Requirements:

Stripe product/price created and matches tiers.ts

Pricing page renders the new tier correctly

Checkout flow works for the onboarding tier

Grace period triggers correctly at expiry

Risks & Mitigations:

Cannibalisation: if onboarding is too generous, users may never upgrade — needs careful limit design

Complexity: adding a 4th self-serve tier increases billing state machine complexity

### M-1D: Substrate Data Migration (Cross-Host) — ⬜ NOT STARTED

| Repo: mmpm-compute | Complexity: High | Est. Sessions: 2–3 | Depends On: M-1B |
| --- | --- | --- | --- |

DATA MIGRATION DOES NOT EXIST. The tier-change service (line 273) says: "Future: LevelDB rsync migration between hosts." Every cross-host tier change (shared→dedicated, dedicated→shared) currently provisions a FRESH EMPTY substrate and abandons the old data. substrate-destroyer.ts runs rm -rf with zero backup. substrate-provisioner.ts always creates an empty /db directory. This means a customer upgrading from Indie to Team LOSES ALL THEIR ATOMS AND EDGES. This milestone builds the migration pipeline: stop → backup → transfer → restore → verify → cutover → cleanup.

Deliverables:

Migration service: src/services/substrate-migration-service.ts

State machine: pending → source_read_only → backing_up → transferring → restoring → verifying → cutting_over → complete (each step persisted to DB)

Backup: graceful container stop → tar -czf the LevelDB directory → store tarball on source host

Transfer: scp tarball from source host to destination host (internal network or public IP)

Restore: untar into new customer directory on destination host → start container

Verify: call /stats on new substrate, compare atom count to pre-migration count

Cutover: update DNS/Traefik to point to new substrate, mark old as decommissioned

Cleanup: after 48h hold period, delete old data and tarball from source host

Schema migration: add substrate_migrations table tracking migration state and audit trail

Wire into tier-change-service.ts: replace "fresh start" comments with migration calls

Snapshot-before-destroy: substrate-destroyer must backup before rm -rf (safety net)

Test Requirements:

Integration: migrate substrate from shared → dedicated host, verify atom count matches

Integration: migrate substrate from dedicated → shared host, verify atom count matches

Crash recovery: kill process at each migration state, verify it resumes correctly

Rollback: if verification fails, revert to source substrate (still available during hold period)

Edge case: migrate substrate with 0 atoms (empty) — should succeed cleanly

Edge case: migrate substrate with 100K+ atoms — verify transfer time and integrity

Edge case: network failure during scp — retry with exponential backoff

Verify Merkle tree integrity on destination (if tree is derived, verify reconstruction)

Risks & Mitigations:

LevelDB consistency: must gracefully stop the container and flush WAL before backup. If the container crashes during backup, the tarball may be corrupt.

Transfer time for large substrates: 100K atoms at ~1KB each = ~100MB. On internal network this is seconds, on public network with SSH this is minutes. Dashboard must show progress.

DNS/Traefik cutover is not instant: there is a window where the old substrate is stopped and the new one is not yet routable. Consider a maintenance page or queue during cutover.

Merkle tree reconstruction: if the Merkle tree is stored in LevelDB, it transfers with the data. If it is derived, it must be rebuilt on the new substrate. Verify which.

The 48h hold period before cleanup is a safety net. If anything goes wrong, roll back by re-pointing DNS to the old substrate.

## Phase 1 Sprint Plan

Sprint 1.1    Build MMPM /stats Endpoint

Investigate:

Read the MMPM service codebase — understand the LevelDB data model, existing routes, auth middleware

How does the bootstrap call currently work? Where is the counter (if any)?

What is the LevelDB directory structure? Can we get size cheaply or do we need to walk the tree?

How does the metering worker currently attempt to get stats? Is it calling an endpoint that doesn't exist?

Check if there's already a /health or /info endpoint we can extend rather than create from scratch

Implement:

GET /stats endpoint: returns { atomCount, bootstrapCount, storageBytesUsed, periodStart, periodEnd }

Bootstrap counter: persist in LevelDB metadata namespace, increment on POST /memory/bootstrap, reset monthly

Storage tracking: either incremental (update on write) or periodic (fs.stat every 10s, cache result)

Bearer auth: same API key as other MMPM endpoints (X-API-Key header)

10-second internal cache to prevent expensive recalculations under rapid polling

Verify:

curl substrate:port/stats with valid API key — returns correct JSON

Create atoms, bootstrap, check /stats reflects changes

Kill and restart the MMPM service — verify counters survive (LevelDB persistence)

Test with empty substrate — returns 0s, not errors

Run full MMPM test suite to ensure no regressions

Session Notes — Sprint 1.1 This is the linchpin of Phase 2. Without /stats, the entire observability stack is blind. The metering worker IS running (we can see usage_metered events in ops for acct_0d5d8526), which means it's firing but probably reporting 0 because there's nothing to query. Once /stats exists, the metering worker, billing status API, and dashboard all light up. The 10s cache is important — the billing status API and dashboard both poll, and we don't want to thrash LevelDB. Storage tracking is the trickiest part: LevelDB compaction can change directory size unpredictably, so incremental tracking on writes is more reliable than periodic fs.stat. Think about what happens during a Merkle proof rebuild — storage could temporarily spike. The counter reset logic needs to align with Stripe billing periods, not calendar months.

Expected Outcome: Every running substrate exposes real-time usage data via authenticated /stats endpoint.

Sprint 1.2    Chain Dedicated Droplet → Substrate Provisioning

Investigate:

Read provisioner.ts (DO API) and substrate-provisioner.ts (SSH + docker-compose) — map their state machines

What happened on April 2 when provisioning failed? Read ops logs and incident data for root cause

How does the substrate_provision_queue schema handle hosting_model? Does it need a new column or is there already a host_type discriminator?

How does Traefik registration work for dedicated hosts vs shared hosts? Different network topology.

What is the cleanup story if a droplet is created but substrate deploy fails? Who owns the orphan?

Implement:

dedicated-provisioner.ts: orchestrator that calls provisioner functions then substrate-provisioner functions sequentially

State machine: pending → droplet_creating → droplet_ready → substrate_deploying → traefik_registering → running

Each state transition persisted to DB — crash at any point and resume from last committed state

Cleanup handler: on failure after droplet_creating, snapshot the droplet and destroy it, credit the customer

Add retry logic with exponential backoff at SSH connection and docker-compose deploy stages (lesson from April 2)

PM2 ecosystem.config.cjs: add dedicated-provisioner as process #15

Verify:

Integration test with mock-do-server + Testcontainers SSH target: full chain completes

Kill process at each state — restart and verify it resumes correctly

Force failure at substrate_deploying stage — verify orphan droplet is cleaned up

Two concurrent dedicated provisions — verify no interference

Full E2E: Team tier checkout → dedicated provision → substrate health check passes

Session Notes — Sprint 1.2 This is the highest-complexity sprint in the entire program. The April 2 failures are a warning: SSH connectivity to fresh droplets is flaky (cloud-init not finished, sshd not yet listening, firewall rules not yet applied). The existing substrate-provisioner already handles SSH retries but may not account for the 60–90 second gap between DO API returning "active" and SSH actually being ready. The dedicated orchestrator needs to poll for SSH readiness explicitly, not just check droplet status. The Traefik registration is different for dedicated hosts — the substrate runs on a different IP, so the Traefik config needs the external IP, not the Docker bridge IP. The cleanup handler is business-critical: a $5–$40/month droplet running with no substrate is pure cost leakage. The snapshot-before-destroy pattern preserves debugging evidence. Consider adding a "provisioning progress" SSE channel so the dashboard can show real-time updates during the 3–5 minute provisioning window.

Expected Outcome: Team/Enterprise checkout creates a dedicated droplet with running substrate in one automated flow.

Sprint 1.3    Design the Onboarding Tier

Investigate:

What do competitors offer as free/trial tiers? (Mem0, Zep, etc.) — research via web

What is the "aha moment" for persistent memory? Is it: remembering across sessions? Merkle-verified recall? Markov prediction?

What minimum atom count demonstrates value without being generous enough to stay forever?

How does the Free/$1 safety net interact with the onboarding tier? Can a user go: signup → onboarding → (doesn't pay) → free safety net?

What conversion hooks work best for developer tools? Time limit? Feature gate? Usage ceiling?

Implement:

Tier specification document: name, price, limits, duration, conversion triggers

Stripe product + price creation for the new tier

tiers.ts: add the new tier to the canonical registry (TierId union, TIERS array, TIER_ORDER)

Pricing page: add the onboarding tier card with appropriate CTA and positioning

Grace period logic: what happens at onboarding expiry? Auto-upgrade? Downgrade to free safety net?

Database: ensure accounts table and substrate_subscriptions handle the new tier_id

Verify:

tiers.ts compiles with new tier, all type checks pass

Stripe product/price exists and matches tiers.ts

Pricing page renders the new tier correctly in all viewport sizes

Checkout flow works for onboarding tier (Stripe test mode)

Expiry/conversion flow works as designed

Session Notes — Sprint 1.3 This sprint is as much product design as it is engineering. The onboarding tier lives in the conversion funnel between "curious visitor" and "paying customer." Too generous and nobody upgrades; too stingy and nobody sees the value. The sweet spot for developer tools is usually: enough to build a real prototype but not enough for production. For MMPM, that might be ~1000 atoms, 50 bootstraps/month, 1 substrate, 14-day trial. The Merkle proof verification and Markov prediction should be unrestricted — those are the differentiators that make people upgrade. The conversion trigger should be a soft nudge at 80% atom usage + a hard gate at limit. Consider a "your memory is getting too big for this tier" message that shows how Indie ($9) removes the ceiling. The interaction with the Free safety net is important: if someone lets their onboarding expire, do they become a Free/$1 safety net customer (atoms preserved 30 days) or do they just lose access? The safety net model is more humane.

Expected Outcome: Onboarding tier designed, Stripe product created, pricing page updated, conversion flow working.

Sprint 1.4    Build Substrate Data Migration

Investigate:

Read tier-change-service.ts fully — map the exact code paths for shared→dedicated and dedicated→shared

Where is the "fresh start" happening? Line 273+ says "Future: LevelDB rsync migration between hosts"

How is LevelDB structured inside the container? Is it one directory or multiple? What about the Merkle tree?

Does MMPM have a backup/restore endpoint, or is file-level backup the only option?

How does substrate-destroyer.ts currently handle the data directory? Read lines 199–218 (rm -rf path)

What is the network topology between shared hosts and dedicated hosts? Can they scp directly?

Implement:

substrate-migration-service.ts: orchestrates the full migration pipeline

State machine: source_read_only → backing_up → transferring → restoring → verifying → cutting_over → complete

Backup step: graceful docker compose stop → tar -czf the /db directory on source host

Transfer step: scp tarball from source to destination (use SSH keys already available from provisioner)

Restore step: untar into new customer directory → docker compose up

Verify step: call /stats on new substrate, compare atomCount to pre-migration snapshot

Cutover step: update Traefik routing to new substrate, mark old as decommissioned

Safety net: substrate-destroyer must now backup before rm -rf (tarball retained 48h)

Schema: substrate_migrations table with source_host, dest_host, state, atom_count_before, atom_count_after

Wire into tier-change-service.ts: shared→dedicated and dedicated→shared now call migration service

Verify:

Migrate a test substrate (shared → dedicated): atom count matches before and after

Migrate back (dedicated → shared): atom count still matches

Kill the migration worker mid-transfer: restart and verify it resumes from last state

Force verification failure: verify rollback re-enables source substrate

Large substrate test: 50K+ atoms, verify transfer completes and integrity holds

substrate-destroyer: verify it now creates a backup before deleting (safety net)

Session Notes — Sprint 1.4 This is the most important infrastructure sprint in the program. Without it, every tier upgrade that crosses host boundaries is a data loss event. The customer pays MORE and loses their memory — that is a trust-destroying experience. The good news: the building blocks exist. SSH keys are already available (provisioner uses them), LevelDB is just files in a bind-mounted directory, graceful shutdown is supported (30s grace period in docker-compose). The migration is fundamentally: stop → tar → scp → untar → start → verify. The hard part is the orchestration and error handling: what if scp fails mid-transfer? What if the new substrate starts but /stats returns a different atom count? What if DNS cutover leaves a gap? The 48h hold period is critical insurance — keep the old substrate available so you can roll back by re-pointing DNS. The Merkle tree is the wildcard: if it is stored in LevelDB, it transfers with the data and you are fine. If it is derived/computed, the new substrate needs to rebuild it on first boot, which could take seconds or minutes depending on atom count. Investigate this BEFORE building the migration — it determines whether the restore step is "untar and start" or "untar, rebuild Merkle, then start." Also: this sprint makes the substrate-destroyer safer by adding backup-before-delete. That is a standalone safety improvement even without the full migration pipeline.

Expected Outcome: Tier changes preserve all customer data. No more data loss on upgrade/downgrade.

PHASE 2    Observability

Wire live data into billing, dashboard, and metering

Customer Trust The metering worker IS running (ops shows usage_metered events for acct_0d5d8526), but the dashboard shows 0 because there is no /stats endpoint to query. This phase closes the gap: customers see their real atom count, bootstrap usage, and storage consumption. Stripe charges accurate overages. The billing status endpoint stops lying.

### M-2A: Wire Live Usage into Billing Status — ✅ SHIPPED

| Repo: mmpm-compute | Complexity: Medium | Est. Sessions: 0.5–1 | Depends On: M-1A |
| --- | --- | --- | --- |

Replace the atomsUsed: 0 and bootstrapsUsed: 0 stubs in GET /api/billing/status with real queries to each customer’s substrate /stats endpoint. Results should be cached briefly to avoid hammering substrates on every dashboard load.

Deliverables:

Compute server calls substrate /stats endpoint (internal Docker network for shared hosts, HTTPS for dedicated)

60-second TTL cache per substrate (in-memory Map with expiry)

Graceful fallback: if substrate is unreachable, return { available: false } not zeroes

Response shape: { atomsUsed, atomsLimit, bootstrapsUsed, bootstrapsLimit, storageMB, storageLimitMB }

Test Requirements:

Unit: cache hit/miss/expiry logic

Integration: mock substrate returning known values, verify billing status reflects them

Fallback: substrate timeout returns unavailable flag, not error

### M-2B: Dashboard Usage Display — ✅ SHIPPED

| Repo: mmpm-website | Complexity: Medium | Est. Sessions: 0.5–1 | Depends On: M-2A |
| --- | --- | --- | --- |

Update the dashboard components to render real usage metrics from the billing status API. Add progress bars, percentage indicators, and warning states when usage approaches tier limits.

Deliverables:

Atom usage bar: current / limit with percentage

Bootstrap usage bar: current / limit with monthly reset indicator

Storage usage bar: current / limit in MB/GB

Warning state at 80% usage (amber), critical state at 95% (red)

Unavailable state when substrate metrics can’t be fetched (distinct from 0)

Test Requirements:

Component tests: render at 0%, 50%, 80%, 95%, 100%, over-limit

Component test: unavailable state shows appropriate message

Snapshot tests for visual regression

### M-2C: Fix Substrate Metering Worker — ✅ SHIPPED

| Repo: mmpm-compute | Complexity: Low–Medium | Est. Sessions: 0.5 | Depends On: M-1A |
| --- | --- | --- | --- |

The metering worker (substrate-metering.ts) is running and firing events (confirmed via ops: usage_metered for acct_0d5d8526), but may be reporting 0 atoms because it cannot query the substrate /stats endpoint. Once M-1A provides /stats, update the metering worker to query real data and report accurate overage events to Stripe Billing Meter.

Deliverables:

Worker queries /stats from each running substrate during daily metering run

Overage calculation: atomsUsed - tierLimit = overage (if positive)

Reports to Stripe Billing Meter (mtr_test_61UOTFtCuKRJEhbFu41KPmxRibChZ29A) with accurate event count

billing_events row logged for each overage report

Test Requirements:

Integration: mock substrate at 150% limit, verify correct overage amount reported

Integration: mock substrate under limit, verify no overage reported

Edge case: substrate unreachable during metering — skip with warning, don’t fail batch

## Phase 2 Sprint Plan

Sprint 2.1    Wire Live Usage into Billing & Dashboard

Investigate:

Read GET /api/billing/status in compute — where exactly are the 0 stubs? What shape does the response have?

How does compute reach substrates on shared hosts? Internal Docker network? Direct port? Service discovery?

How does compute reach substrates on dedicated hosts? HTTPS with Traefik? Direct SSH tunnel?

What happens to billing status when a substrate is being provisioned, upgrading, or in grace period?

Does the dashboard currently poll billing/status on an interval, or only on page load?

Implement:

Compute: replace 0 stubs with real /stats calls to each substrate

Shared host: call substrate via internal Docker bridge (http://substrate-{id}:port/stats)

Dedicated host: call via HTTPS through Traefik (https://customer.memory.kiwi/stats)

60s TTL in-memory cache per substrate — Map<substrateId, { data, expiresAt }>

Graceful fallback: if /stats unreachable, return { available: false, reason: "substrate unreachable" }

Dashboard: add progress bars for atoms, bootstraps, storage with warning at 80% and critical at 95%

Dashboard: "unavailable" state distinct from "0 usage" — different UI treatment

Verify:

Billing status API returns real numbers for a substrate with known data

Dashboard shows progress bars with correct percentages

Dashboard shows amber at 80%, red at 95%

Dashboard shows "unavailable" when substrate is down, not "0"

Cache works: rapid requests don't hammer substrates

All component tests pass, snapshot tests updated

Session Notes — Sprint 2.1 This sprint collapses M-2A and M-2B into one session because they're tightly coupled — you can't verify the billing status wire-up without the dashboard rendering it. The key insight is that there are TWO network paths to substrates (Docker bridge for shared, HTTPS for dedicated) and the compute server needs to route correctly based on the hosting_model. This is an early integration test for the dedicated droplet chain (M-1B): even before the chain is built, we need to handle "what if the substrate is on a dedicated host?" The cache TTL of 60s is a balance: too short and we hammer substrates, too long and the dashboard feels stale. The "unavailable" vs "0" distinction is a trust signal — a customer seeing "0 atoms" when they know they stored 500 will file a support ticket. "Substrate unreachable" is honest and actionable.

Expected Outcome: Dashboard shows real, live usage data for all active substrates. No more zeros.

Sprint 2.2    Fix Metering Worker Overage Reporting

Investigate:

Read substrate-metering.ts — how does it currently query substrates? What does it send to Stripe Meter?

Ops shows usage_metered events for acct_0d5d8526 — is it reporting 0 atoms or actual counts?

What is the Stripe Billing Meter configuration? Event name, aggregation, default price?

How does the metering worker determine tier limits? Does it read from tiers.ts or from the DB?

What happens when the metering worker encounters a substrate in grace period or being deprovisioned?

Implement:

Update metering worker to call /stats on each running substrate (reuse Sprint 2.1's routing logic)

Overage calculation: atomsUsed - tierLimit = overage events to report

Report to Stripe Billing Meter (mtr_test_61UOTFtCuKRJEhbFu41KPmxRibChZ29A) with meter_event API

Log each report to billing_events table for audit trail

Skip substrates in grace_period or deprovisioning state — no overage charges during wind-down

Verify:

Mock substrate at 150% of Indie limit — verify correct overage amount in Stripe Meter

Mock substrate at 50% limit — verify NO overage reported

Substrate unreachable during metering — skip with warning, don't fail the entire batch

Check billing_events table for audit rows

Stripe dashboard shows meter events with correct quantities

Session Notes — Sprint 2.2 The metering worker is already running and firing events — we saw this in ops. The question is: what is it reporting? If it's reporting 0 atoms because it can't query /stats, then Stripe is receiving zero-value meter events, which means no overage invoices are generated. This is a silent revenue leak. Once M-1A provides the /stats endpoint, this sprint should be quick — the worker skeleton exists, it just needs real data. The Stripe Billing Meter API is idempotent on event_name + timestamp, so there's no risk of double-billing if the worker runs twice. The audit trail in billing_events is important for customer disputes: "you charged me $X in overage" — "here's the per-day atom count and the exact Stripe meter events." Consider adding a weekly overage summary email to customers approaching their limit as a Phase 3 email template.

Expected Outcome: Metering worker reports accurate overage to Stripe. Revenue is captured correctly.

PHASE 3    Email & Lifecycle

Give customers professional lifecycle communications

### M-3A: Email Service on Website — ⬜ NOT STARTED

| Repo: mmpm-website | Complexity: Medium | Est. Sessions: 1 | Depends On: None |
| --- | --- | --- | --- |

Set up Resend as a proper email service in the website repo. Create typed email templates for all customer lifecycle events. This service becomes the single email hub for the platform (except auth magic links which remain in compute).

Deliverables:

src/lib/email-service.ts: Resend wrapper with typed template selection

HTML email templates (React Email or inline HTML): welcome, subscription confirmed, payment failed, grace period warning (7d and 2d before expiry), key rotation complete, cancellation confirmed, account deletion notice

Template preview endpoint (dev only): GET /api/internal/email-preview?template=welcome

Email service respects a kill switch env var (EMAIL_ENABLED=false) for testing

Test Requirements:

Unit: each template renders valid HTML with correct variable interpolation

Unit: Resend mock verifies correct from/to/subject/html

Unit: kill switch prevents actual sends in test environment

### M-3B: Webhook-Triggered Lifecycle Emails — ⬜ NOT STARTED

| Repo: Both | Complexity: Medium | Est. Sessions: 1 | Depends On: M-3A |
| --- | --- | --- | --- |

Compute handles Stripe webhooks and state transitions. When an event occurs that should trigger an email, compute calls a new website internal endpoint to send it. The endpoint is authenticated with INTERNAL_SERVICE_KEY to prevent unauthorized sends.

Deliverables:

Website: POST /api/internal/send-email endpoint (INTERNAL_SERVICE_KEY auth)

Request body: { template: string, to: string, data: Record<string, any> }

Compute: call website endpoint on: subscription_created, payment_failed, grace_period_started, substrate_provisioned, key_rotation_complete, subscription_cancelled

Idempotency: include eventId in request, website deduplicates within 1-hour window

Error handling: compute logs but does not retry failed email sends (fire-and-forget)

Test Requirements:

Integration: compute fires event, website sends correct template

Security: requests without INTERNAL_SERVICE_KEY return 401

Idempotency: duplicate eventId within window returns 200 without re-sending

Risks & Mitigations:

Website being down blocks email sends — acceptable for v1 (fire-and-forget), but consider a dead-letter queue for v2

### M-3C: Team Inquiry Notification — ⬜ NOT STARTED

| Repo: mmpm-website | Complexity: Low | Est. Sessions: 0.5 | Depends On: M-3A |
| --- | --- | --- | --- |

Wire the team inquiry form to send you an email via Resend with the prospect’s details, replacing the current stdout logging.

Deliverables:

Update POST /api/team-inquiry to use email service

Send notification to configured CONTACT_EMAIL with company name, email, message, tier interest

Auto-reply to prospect confirming receipt (simple template)

Test Requirements:

Integration: form submission triggers two emails (notification + auto-reply)

Validation: missing required fields return 400 with specific errors

## Phase 3 Sprint Plan

Sprint 3.1    Build Email Service + Templates

Investigate:

Read current auth magic link email code in compute — what pattern does it use? What Resend config exists?

Does the website already have Resend installed? Check package.json and .env for RESEND_API_KEY

What email templates do customers of competing products (Mem0, Zep) receive? What's the baseline expectation?

Review Resend's React Email library — is it worth using or is inline HTML simpler for our template count?

What are the transactional email regulations? CAN-SPAM requires unsubscribe link and physical address.

Implement:

src/lib/email-service.ts: Resend wrapper with typed template selection and EMAIL_ENABLED kill switch

Templates: welcome, subscription_confirmed, payment_failed, grace_period_7d, grace_period_2d, key_rotation_complete, cancellation_confirmed, account_deletion_notice

Each template: responsive HTML, brand colors (#1B3A5C, #2E5984), logo, unsubscribe footer

Dev-only preview endpoint: GET /api/internal/email-preview?template=welcome&mock=true

POST /api/internal/send-email: INTERNAL_SERVICE_KEY auth, { template, to, data } body

Idempotency: eventId-based deduplication with 1-hour window (in-memory Set with TTL)

Verify:

Each template renders valid HTML (use email client preview tool)

Resend mock verifies correct from/to/subject/html for each template

Kill switch prevents sends when EMAIL_ENABLED=false

INTERNAL_SERVICE_KEY auth: 401 without key, 200 with key

Idempotency: duplicate eventId returns 200 without re-sending

Preview endpoint shows each template with mock data

Session Notes — Sprint 3.1 Email is a trust multiplier. A SaaS product that sends no emails after signup feels abandoned. The minimum viable set is: welcome (confirms they exist in the system), payment failed (prevents involuntary churn), and grace period warning (gives them a chance to save their data). The key design decision is React Email vs inline HTML. React Email is nicer to maintain but adds a build step. For 8 templates, inline HTML with a shared header/footer is simpler and has fewer failure modes. The INTERNAL_SERVICE_KEY pattern is important: compute triggers emails but website sends them. This separation means compute doesn't need Resend credentials. The idempotency window prevents Stripe webhook retries from sending duplicate emails. One hour is generous — Stripe retries up to 3 times over 24 hours, but the same eventId means the same event.

Expected Outcome: Email service operational with 8 templates. Compute can trigger email sends via internal API.

Sprint 3.2    Wire Webhooks to Lifecycle Emails

Investigate:

Map all Stripe webhook events to email templates: which webhook triggers which email?

Read the existing webhook handler in compute — where are the event handlers? What events are already handled?

What state transitions in the compute state machine should trigger emails? (e.g., grace_period_started)

Is INTERNAL_SERVICE_KEY already shared between repos? Check compute .env and website .env

What is the failure mode if the website is down when compute tries to send an email?

Implement:

Compute webhook handlers: after processing each Stripe event, POST to website /api/internal/send-email

Map: invoice.paid → subscription_confirmed, invoice.payment_failed → payment_failed, customer.subscription.deleted → cancellation_confirmed

State machine hooks: grace_period_entered → grace_period_7d, key_rotation completed → key_rotation_complete

Fire-and-forget: compute logs email send failures but does not retry or block on them

Wire team inquiry form to email service (M-3C: notification to CONTACT_EMAIL + auto-reply to prospect)

Verify:

Trigger each webhook event in Stripe test mode — verify correct email is sent

Grace period state transition triggers email

Key rotation completion triggers email

Website down: compute logs error but continues processing webhooks

Team inquiry form sends both notification and auto-reply

Session Notes — Sprint 3.2 This sprint connects two systems that were designed separately. The risk is timing: Stripe webhooks arrive asynchronously, and the compute webhook handler must process the business logic (update DB, trigger provisioning) BEFORE sending the email. If the email send happens before the DB update, and the webhook handler crashes, the customer gets a "subscription confirmed" email but the DB doesn't reflect it. Always: DB first, email second, fire-and-forget. The team inquiry notification (M-3C) is a quick win that adds sales lead capture. Consider adding a Slack webhook too for real-time alerts on new inquiries. The fire-and-forget model means some emails will be lost if the website is down during a webhook. For v1 this is acceptable; for v2, consider a simple outbox table in compute that retries unsent emails.

Expected Outcome: Every lifecycle event triggers the correct email. Sales inquiries notify the team.

PHASE 4    CI/CD & Deployment

Automate the deployment pipeline for both repositories

Parallel Phase This phase has no dependencies on Phases 0–3. It can be started immediately and worked on in parallel. Every manual deploy is a risk of human error and a tax on development velocity.

### M-4A: GitHub Actions — Website — 🔶 PARTIAL

| Repo: mmpm-website | Complexity: Medium | Est. Sessions: 0.5–1 | Depends On: None |
| --- | --- | --- | --- |

Create a GitHub Actions workflow that on push to main: runs the preflight suite (format + lint + typecheck + test + build), builds and pushes a Docker image to the registry, then SSHes into the production droplet to pull and restart.

Deliverables:

.github/workflows/deploy.yml: checkout → npm run preflight → Docker build + tag with commit SHA → docker push → SSH deploy → health check

GitHub secrets: DEPLOY_SSH_KEY, DEPLOY_HOST, DOCKER_HUB_TOKEN, DOCKER_HUB_USER

Deploy script on server: docker pull, docker-compose up -d, wait for /api/health 200

Rollback instruction: manual docker-compose up with previous SHA tag

Slack/email notification on deploy success or failure (optional)

Test Requirements:

The workflow itself runs npm run preflight as a gate (lint + typecheck + test + build)

Health check after deploy confirms the new version is serving

### M-4B: GitHub Actions — Compute — 🔶 PARTIAL

| Repo: mmpm-compute | Complexity: Medium | Est. Sessions: 0.5–1 | Depends On: None |
| --- | --- | --- | --- |

Same pattern as website but for the compute backend. Additional complexity: must run database migrations before restarting PM2 processes (new code may expect new schema).

Deliverables:

.github/workflows/deploy.yml: checkout → npm run test:all → SSH deploy

Deploy script: git pull → npm install → npm run db:migrate:prod → pm2 reload ecosystem.config.cjs --env production → health check

Migration safety: if migration fails, abort deploy (do not reload PM2)

Zero-downtime: PM2 reload (not restart) for graceful process replacement

Test Requirements:

npm run test:all as CI gate (unit + integration + security + property)

Post-deploy health check on /api/health

Risks & Mitigations:

Migration failure with partial apply — use node-pg-migrate’s built-in transaction wrapping

PM2 reload during active provisioning — process guards handle graceful shutdown on SIGTERM

### M-4C: Docs Auto-Regeneration — ⬜ NOT STARTED

| Repo: mmpm-website | Complexity: Low | Est. Sessions: 0.5 | Depends On: M-4A |
| --- | --- | --- | --- |

Add a step to the website deploy workflow that runs npm run generate-docs after build, ensuring documentation stays fresh on every deploy.

Deliverables:

Add generate-docs step to deploy workflow (after build, before Docker image creation)

Remove or simplify the stubbed docs-hook endpoint (no longer needed)

Test Requirements:

npm run generate-docs completes without errors in CI

## Phase 4 Sprint Plan

Sprint 4.1    CI/CD for Both Repos

Investigate:

What is the current deploy process? SSH + git pull? Docker? Document the manual steps.

Does the website build require env vars at build time? (NEXT_PUBLIC_* vars are baked into the bundle)

Does compute have a preflight script? What does npm run test:all cover?

How are database migrations currently run? Manually via SSH? Part of a deploy script?

What is the Docker registry setup? Docker Hub? DigitalOcean Container Registry? GitHub Packages?

Implement:

Website .github/workflows/deploy.yml: checkout → npm run preflight → Docker build (inject env vars) → docker push with commit SHA tag → SSH deploy → health check

Compute .github/workflows/deploy.yml: checkout → npm run test:all → SSH deploy → npm run db:migrate:prod → pm2 reload → health check

GitHub secrets for both repos: DEPLOY_SSH_KEY, DEPLOY_HOST, DOCKER_HUB_TOKEN (if Docker Hub)

Deploy scripts on server: pull image, run migrations (compute only), restart services, health check

Rollback instructions in each workflow as comments

Docs auto-generation step in website workflow (M-4C)

Verify:

Push to main on website repo → GitHub Actions runs → new version deployed → health check passes

Push to main on compute repo → tests pass → migrations run → PM2 reloads → health check passes

Deliberate test failure blocks deploy (CI gate works)

Migration failure aborts deploy (compute doesn't reload PM2 on failed migration)

Rollback: manually deploy previous SHA tag and verify it works

Session Notes — Sprint 4.1 CI/CD is a velocity multiplier. Every manual deploy costs 15–30 minutes and carries risk of forgetting a step (run migrations, clear cache, check health). The key design choice is Docker vs git-pull deploy. Docker is cleaner for the website (immutable artifact, rollback by tag), but compute is more complex because PM2 manages 14 processes that need graceful reload. For compute, git pull + PM2 reload is simpler and already proven in the current manual process. The migration-before-reload order is critical: new code may expect new columns. If the migration fails, aborting before PM2 reload means the old code continues running against the old schema — safe. The docs auto-generation (M-4C) is a freebie in this sprint: just add npm run generate-docs after build in the website workflow. Consider adding a Slack/email notification on deploy success/failure — useful when you're not watching the Actions tab.

Expected Outcome: Both repos deploy automatically on push to main. No more manual SSH deploys.

PHASE 5    Hardening & Polish

Final sweep before opening the doors to customers

### M-5A: Activate Nginx Rate Limiting — ⬜ NOT STARTED

| Repo: Infrastructure (production server) | Complexity: Low | Est. Sessions: 0.5 | Depends On: None |
| --- | --- | --- | --- |

The nginx config already has a rate limiting framework in comments. Activate it with sensible defaults to protect against abuse and DDoS.

Deliverables:

Auth endpoints: 10 req/min per IP (limit_req_zone + limit_req)

API endpoints: 60 req/min per IP

Webhook endpoints: exempt (Stripe, GitHub need reliable delivery)

Static assets: no limit (served from cache)

Custom 429 error page with retry-after header

Test Requirements:

Manual: verify rate limits trigger on rapid requests

Manual: verify webhook endpoints are not rate-limited

Manual: verify legitimate browsing is not impacted

### M-5B: E2E: Per-Tier Customer Journey Tests — ⬜ NOT STARTED

| Repo: mmpm-website + mmpm-compute | Complexity: High | Est. Sessions: 2–3 | Depends On: M-2B, M-3B, M-1D |
| --- | --- | --- | --- |

Write Playwright tests that exercise the complete customer lifecycle for EACH product tier. Each tier has different provisioning paths (shared vs dedicated), different resource limits, different pricing, and potentially different features. A single generic E2E test is not enough — we need to verify that every product we sell actually works end-to-end. This includes tier upgrade/downgrade with data migration (M-1D), proving atoms survive the move.

Deliverables:

tests/e2e/tier-indie.spec.ts: Indie ($9) → shared host, 10K atoms, full journey

tests/e2e/tier-pro.spec.ts: Pro ($29) → shared host, 100K atoms, full journey

tests/e2e/tier-team.spec.ts: Team ($79) → dedicated host, 500K atoms, full journey

tests/e2e/tier-upgrade.spec.ts: Indie → Pro (shared→shared), Indie → Team (shared→dedicated) — verify atoms survive migration

tests/e2e/tier-downgrade.spec.ts: Team → Pro (dedicated→shared) — verify atoms survive

tests/e2e/tier-onboarding.spec.ts: Onboarding tier journey + conversion to Indie

Each test covers: signup → login → checkout → provisioning → dashboard → create atoms → verify usage metrics → email notifications → (for upgrade tests: trigger upgrade, verify atoms preserved) → cancel → grace period

Test infrastructure: Stripe test mode, mock-do-server, email capture

CI integration: full suite runs nightly, smoke test (Indie only) runs on every deploy

Test Requirements:

These ARE the tests — they validate every product the business sells

Each tier test must pass independently and in sequence

Upgrade/downgrade tests must verify atom count before and after migration

Risks & Mitigations:

Test flakiness from timing-dependent provisioning — use polling with generous timeouts

Stripe test mode has rate limits — use a dedicated test Stripe account

Dedicated host provisioning in test: mock-do-server must simulate the full chain (M-1B)

Migration tests depend on M-1D — if migration is not built, upgrade tests will show data loss

### M-5C: Developer Portal — ⬜ NOT STARTED

| Repo: mmpm-website | Complexity: Medium | Est. Sessions: 1 | Depends On: None |
| --- | --- | --- | --- |

Transform the /developers stub into a real page with API documentation, MCP integration guide, quickstart snippets, and authentication instructions. This is the onboarding ramp for technical customers.

Deliverables:

Quickstart guide: sign up → get API key → configure Claude Desktop → first memory

API reference: all MMPM endpoints with request/response examples

MCP integration guide: claude_desktop_config.json setup, tool list, SSE events

Code examples: JavaScript, Python, curl for common operations

Authentication docs: API key usage, key rotation, security best practices

Test Requirements:

Page renders correctly, no broken links

Code snippets are syntactically valid (automated linting)

### M-5D: Contact Page & Ops Graduation — ⬜ NOT STARTED

| Repo: Both | Complexity: Low | Est. Sessions: 0.5 | Depends On: M-3A |
| --- | --- | --- | --- |

Wire up the contact page stub to the email service. Graduate the ops inference agent from shadow mode to active flagging of at-risk accounts.

Deliverables:

Contact page: form → email via Resend (same service as team inquiry)

Ops agent: flag accounts with payment failures > 7 days, usage > 90% of limits, or substrate health checks failing — log to ops dashboard for human review

Test Requirements:

Contact form sends email correctly

Ops agent flags test accounts with known risk signals

## Phase 5 Sprint Plan

Sprint 5.1    Security Hardening + SEO

Investigate:

Read current nginx config on the production droplet — where are the commented-out rate limit zones?

What rate limits does Stripe impose on webhook delivery? Ensure we don't accidentally rate-limit Stripe.

Check Google Search Console — is the domain verified? Is there a sitemap submission?

Test /faq with Google Rich Results Test — does the FAQPage JSON-LD validate?

Are there any existing 429 responses in nginx access logs from the current config?

Implement:

Nginx rate limiting: 10/min on /auth/*, 60/min on /api/*, exempt /api/webhooks/*

Custom 429 response page with Retry-After header

Google Search Console: verify domain, submit sitemap.xml

Add Google site verification meta tag (or DNS TXT record)

Fix any structured data issues found by Rich Results Test

Verify:

rapid curl to /auth/login triggers 429 after 10 requests in 60s

Stripe webhook delivery is not rate-limited (test with Stripe CLI)

Normal browsing is unaffected

Google Search Console shows sitemap submitted, no errors

Rich Results Test passes for /faq

Session Notes — Sprint 5.1 These two items are bundled because they're both small, infrastructure-level changes with no code dependencies. Rate limiting is defensive infrastructure — without it, a single bot can overwhelm the auth endpoints and burn CPU on argon2 hashing. The 10/min on auth is conservative but safe; increase only if legitimate users hit it (monitor 429 rates in logs). Exempting webhooks is critical — Stripe will retry failed deliveries and if we rate-limit them, we'll miss real payment events. SEO is a business priority: the site has good content (FAQ with JSON-LD, blog posts, docs) but zero organic traffic because Google hasn't indexed it. Submitting the sitemap is table stakes. The FAQPage schema is optimized for AI answer engines (Google AI Mode, Perplexity) which cite sources — this is marketing for an AI-adjacent product.

Expected Outcome: Rate limits active. Site indexed by Google. FAQ appears in rich results.

Sprint 5.2    E2E Customer Journey Test

Investigate:

What Playwright configuration already exists in both repos? Any existing E2E tests?

How does Stripe test mode interact with Playwright? Can we use Stripe test clocks for time-dependent flows?

How do we capture emails in test? Resend test mode? Mailhog? Ethereal?

What is the provisioning latency in test environment? Can we use mock-do-server to speed it up?

Does the current test infrastructure support running both website and compute simultaneously?

Implement:

tests/e2e/customer-journey.spec.ts: signup → magic link login → checkout (Stripe test card) → provisioning wait → dashboard shows substrate → usage metrics visible → key rotation → cancel

Test infrastructure: Stripe test mode, mock-do-server for provisioning, email capture via Resend test mode

Polling helpers: wait for provisioning to complete, wait for dashboard to show metrics

CI integration: optional step in deploy workflow, gated by RUN_E2E=true env var

Test data cleanup: after test run, cancel Stripe subscription and clean up test account

Verify:

The test passes end-to-end in a clean environment

The test fails meaningfully when something is broken (not a false pass)

The test runs in under 5 minutes (with mock-do-server)

CI can run it without manual intervention

Test data is cleaned up — no orphan Stripe subscriptions

Session Notes — Sprint 5.2 This is the final confidence gate. If this test passes, the platform works end-to-end. If it fails, you know exactly where in the journey the break is. The biggest challenge is timing: provisioning takes 30s–60s even with mocks, Stripe webhook delivery is asynchronous, and email delivery is fire-and-forget. Use generous polling timeouts (2min for provisioning, 30s for dashboard updates) and assertion retries. The mock-do-server is essential — running this test against real DO would be slow and expensive. Stripe test clocks are useful for testing grace period and billing cycle flows without waiting real days. This test should NOT be required for every deploy in CI (too slow and flaky), but should run on a nightly schedule and on-demand before releases. Consider recording the test run as a video (Playwright supports this) for debugging failed CI runs.

Expected Outcome: Automated test validates the full customer lifecycle. Runs on every release candidate.

Sprint 5.3    Developer Portal + Contact Page + Ops Graduation

Investigate:

What does the /developers stub currently render? Is there a layout to extend?

What MMPM API endpoints should be documented? List them from the service code.

What does the MCP integration guide need? What does a claude_desktop_config.json look like?

What risk signals does the ops-inference worker currently detect? What is it doing in shadow mode?

Is there a contact page stub already or does it need to be created from scratch?

Implement:

Developer portal: quickstart guide, API reference, MCP integration guide, code examples

Contact page: form with name/email/message, wired to email service (Resend)

Ops graduation: promote ops-inference from shadow mode to active flagging

Ops flags: payment_failed > 7d, usage > 90%, substrate health check failing

Ops dashboard: surface flagged accounts for human review

Verify:

Developer portal: all links work, code snippets are syntactically valid

Contact form sends email to CONTACT_EMAIL

Ops agent correctly flags a test account with payment failure > 7 days

Ops agent does NOT flag healthy accounts (no false positives)

Full manual walkthrough: "as a new developer, can I go from /developers to running memory in 15 min?"

Session Notes — Sprint 5.3 This is the polish sprint. The developer portal is the conversion ramp for technical buyers — if they can't figure out how to integrate in 15 minutes, they'll leave. The quickstart should be opinionated: "here is exactly the 5-step path to your first memory." Not a reference manual. The MCP integration guide is especially important because MMPM's MCP-native approach is a differentiator — show a side-by-side of "with MCP" vs "with REST API" to demonstrate the simplicity. The ops graduation is a business health monitor: when real customers start paying, you need to know immediately if someone's payment fails or their substrate goes unhealthy. Shadow mode was the right call during development (learning what signals matter), but now it's time to act on them. Consider a weekly ops summary email to yourself showing: accounts at risk, revenue at risk, substrates unhealthy.

Expected Outcome: Developer onboarding is self-serve. Contact page works. Ops monitors customer health proactively.

PHASE 6    Pre-Launch Checklist

Switch from test to live — only after all engineering is complete

Why This Is Last The engineering phases (0–5) build and harden the product using Stripe test mode. This is intentional — test mode means zero financial risk during development. Once the engineering is done and the E2E test passes, this phase switches to live Stripe keys and gets the site indexed by Google. These are the final steps before opening the doors.

### PL-1: Stripe: Go Live (Test → Production) — ⬜ NOT STARTED

| Repo: mmpm-compute (Stripe dashboard + .env) | Complexity: Medium | Est. Sessions: 1–2 | Depends On: All engineering phases complete |
| --- | --- | --- | --- |

The ENTIRE Stripe catalog is in test mode. Every product, price, subscription, and the billing meter use test keys (sk_test_, mtr_test_). No real payments can be processed. This milestone recreates the canonical products in live mode, switches API keys, archives all test artifacts, and merges ~19 duplicate customers.

Deliverables:

Create 5 live-mode products in Stripe: Free ($1), Indie ($9), Pro ($29), Team ($79), Overage Atoms

Create matching live-mode prices for each product (monthly recurring + overage metered)

Create a live-mode Billing Meter for atom overage ($0.001/atom)

Update compute .env: STRIPE_SECRET_KEY → sk_live_, all STRIPE_PRICE_* and STRIPE_PRODUCT_* to live IDs

Update compute .env: STRIPE_WEBHOOK_SECRET to live-mode signing secret, STRIPE_METER_ATOM_OVERAGE to live meter

Update website .env: STRIPE_PUBLISHABLE_KEY → pk_live_

Archive all 9 legacy test products and cancel all 17 test subscriptions

Merge ~19 duplicate customer records

Document every change in a Stripe go-live audit log

Test Requirements:

Live-mode: checkout flow completes with a real card (use $1 Free tier for safety)

Live-mode: webhook delivery works (Stripe Dashboard event log)

Live-mode: billing meter accepts overage events

tiers.ts stripePriceEnvKey values match live Stripe price IDs

No test-mode products remain active. No duplicate customer emails.

Grep codebase for hardcoded test IDs (sk_test_, mtr_test_, price_test) — zero matches

Risks & Mitigations:

Switching to live keys means real charges — test carefully before going public

Webhook endpoint URL must be registered in live mode (separate signing secret from test)

If any code hardcodes test price IDs instead of reading from env, checkout breaks silently

### PL-2: Google Search Console + Indexation — ⬜ NOT STARTED

| Repo: mmpm-website (+ Google Search Console) | Complexity: Low | Est. Sessions: 0.5 | Depends On: PL-1 |
| --- | --- | --- | --- |

The site has correct robots.txt and a dynamic sitemap.xml but is completely invisible to Google. Zero organic discovery. This milestone registers the site, submits the sitemap, and ensures all pages are crawlable. Indexation takes days to weeks — submit as soon as Stripe is live so organic traffic starts arriving during the soft launch.

Deliverables:

Register parametric-memory.dev in Google Search Console, verify domain ownership

Submit sitemap.xml, request indexing of key pages (/, /pricing, /faq, /blog, /docs)

Test all pages with Google Rich Results Test — fix any FAQPage JSON-LD issues

Register with Bing Webmaster Tools (covers Bing, Yahoo, DuckDuckGo)

Set up weekly monitoring for crawl errors and indexation progress

Test Requirements:

Google Search Console shows domain verified and sitemap submitted

Rich Results Test passes for /faq with valid FAQPage schema

No crawl errors reported in Search Console

### PL-3: Re-implement TOTP Two-Factor Authentication — ⬜ NOT STARTED

| Repo: Both (website + compute) | Complexity: Medium | Est. Sessions: 1–2 | Depends On: PL-1 (Stripe live), all engineering complete |
| --- | --- | --- | --- |

TOTP was removed in M-0B to clear the decks for engineering. Now that all features are built and tested, re-implement TOTP properly. The compute backend still has the TOTP endpoints (enrollment, challenge, recovery, sudo). The website needs: login TOTP challenge page, sudo elevation for sensitive actions, security settings for enrollment, and the admin dashboard nudge. This time, implement against a fully working system with real E2E tests covering the TOTP flow.

Deliverables:

Restore /auth/totp/page.tsx: login TOTP challenge (or rewrite from the git history)

Restore /auth/callback/route.ts: totpRequired redirect to /auth/totp

Restore /api/auth/totp/route.ts: proxy TOTP challenge/recovery to compute

Restore /api/auth/sudo/route.ts: sudo token issuance after TOTP verification

Restore SudoChallenge.tsx: TOTP dialog for sensitive actions (key rotation, cancel, destroy)

Restore SecurityClient.tsx: TOTP enrollment wizard (QR scan, confirm code, backup codes)

Re-add totpEnrolled prop flow through admin/page.tsx → AdminClient.tsx → components

Re-add TOTP nudge banner on dashboard for accounts without 2FA

Update /terms/page.tsx: re-add TOTP reference

Add E2E test: signup → enable TOTP → logout → login with TOTP → sudo action with TOTP

Test Requirements:

E2E: full TOTP enrollment flow (QR scan, confirm code, backup codes displayed)

E2E: login with TOTP enabled account — magic link + TOTP challenge = session

E2E: sudo elevation — TOTP code required for key rotation, cancel, destroy

E2E: recovery code login when TOTP device is lost

E2E: disable TOTP from security settings (requires current TOTP code)

Unit: SudoChallenge validates 6-digit codes, handles errors correctly

Integration: TOTP challenge/recovery proxied correctly to compute

Risks & Mitigations:

Compute TOTP endpoints may have drifted during engineering — verify they still work before building UI

Git history has the old implementation for reference, but it may not apply cleanly after other changes

## Pre-Launch Sprint Plan

Sprint PL.1    Stripe: Go Live

Investigate:

Audit the compute codebase for any HARDCODED test-mode price IDs or product IDs (grep for sk_test_, price_test, mtr_test_)

Check webhook endpoint registration — live mode uses a separate signing secret from test mode

Verify Stripe Billing Meter code references STRIPE_METER_ATOM_OVERAGE env var, not a hardcoded ID

Check if the Stripe account has completed live-mode onboarding (bank account, identity verification)

Cross-reference each product with tiers.ts stripePriceEnvKey / stripeProductEnvKey values

List all Stripe-dependent code paths: checkout, webhook handler, billing status, metering worker, portal link

Implement:

In Stripe Dashboard: create 5 live-mode products matching the test catalog exactly

Create matching live-mode prices (monthly recurring) and live-mode Billing Meter ($0.001/atom)

Register a live-mode webhook endpoint in Stripe Dashboard (same URL, new signing secret)

Update compute .env: sk_live_, pk_live_, all price/product IDs, webhook secret, meter ID

Update website .env: pk_live_

Archive 9 legacy test products, cancel 17 test subscriptions, merge ~19 duplicate customers

Restart all PM2 processes to pick up new env vars

Document every change in a go-live audit log (spreadsheet)

Verify:

Real card checkout on $1 Free tier — payment succeeds, subscription appears in Stripe live dashboard

Webhook delivery in live mode — check Stripe Dashboard event log, verify compute processes the event

Billing meter accepts a test overage event in live mode

Full E2E test passes against live Stripe (or re-run with live keys in test env)

No hardcoded test IDs remain: grep -r "sk_test_\|mtr_test_\|price_test" returns zero matches in src/

Session Notes — Sprint PL.1 This is the moment the business becomes real. Every Stripe-dependent code path must be verified against live keys. The scariest failure mode is the webhook secret — live mode uses a different signing secret than test mode. If you switch the API key but forget the webhook secret, every webhook verification fails silently and nothing works (no provisioning, no billing events, no emails). Do NOT combine this with code changes. Switch Stripe keys in isolation so you know the only variable is the key change. Keep .env.test pointing to test keys so development continues safely. The audit log is insurance: if anything breaks in the first week of live mode, you can trace exactly what changed. After this sprint, a real customer can pay you real money. Treat it with that gravity.

Expected Outcome: Stripe is in live mode. Real payments flow. Revenue collection begins.

Sprint PL.2    Get Indexed by Google

Investigate:

Is parametric-memory.dev already verified in Google Search Console? Check DNS TXT records.

Does the site SSR or CSR key pages? Googlebot needs server-rendered HTML.

Test with Google URL Inspection tool — can Googlebot render the homepage?

Check for accidental noindex meta tags or X-Robots-Tag headers

Are there canonical URL issues? (www vs non-www, http vs https redirects)

Implement:

Register parametric-memory.dev in Google Search Console

Add DNS TXT record for domain verification

Submit sitemap.xml via Search Console

Request indexing of priority pages: /, /pricing, /faq, /blog, /docs

Register with Bing Webmaster Tools (free, covers Bing + Yahoo + DuckDuckGo)

Verify:

Search Console shows domain verified

Sitemap submitted with no errors

URL Inspection shows indexing requested for key pages

Rich Results Test passes for /faq (FAQPage JSON-LD)

Session Notes — Sprint PL.2 30 minutes of active work, multi-week tail. Google indexation takes 3–14 days after sitemap submission. The most likely reason for zero current indexation is simply that nobody submitted the sitemap — the site has all the right fundamentals (robots.txt, sitemap.xml, SSR, JSON-LD). Next.js App Router SSRs by default, so Googlebot should see full content. But verify with URL Inspection — if pages are blank to Googlebot, there's a rendering issue. For an AI-memory product, the FAQPage schema is especially valuable: Google AI Mode and Perplexity cite sources with structured data. This is free marketing. Submit to Bing too — it's often overlooked but covers three search engines.

Expected Outcome: Site submitted to Google and Bing. Indexation begins. Organic discovery within 2 weeks.

Sprint PL.3    Re-implement TOTP

Investigate:

Check compute TOTP endpoints still work: POST /api/auth/totp/enrol, /enrol/confirm, /challenge, /recover

Check if any compute endpoints now REQUIRE sudoToken that was removed in M-0B — restore the check

Read git history for the deleted website files — can they be restored cleanly or do they need rewriting?

Has the admin dashboard structure changed since M-0B? Will the old prop drilling pattern still fit?

Review the SudoAction type — are there new sensitive actions added during engineering that need TOTP gating?

Implement:

Restore (or rewrite) the files removed in M-0B, adapted to current codebase state. Recovery command: git checkout totp-last-active -- src/path/to/file.tsx (tag created before M-0B deletion)

Login flow: /auth/callback checks totpRequired → redirect to /auth/totp → challenge → session cookie

Sudo flow: SudoChallenge component → POST /api/auth/sudo → sudoToken for sensitive actions

Security settings: enrollment wizard with QR, confirm, backup codes

Dashboard: totpEnrolled prop, nudge banner for accounts without 2FA

Add E2E Playwright test covering the full TOTP lifecycle

Verify:

Full TOTP enrollment: QR scan → confirm code → backup codes displayed

Login with TOTP: magic link + TOTP code = session (no session without TOTP)

Sudo elevation: key rotation, cancel, destroy all require TOTP code

Recovery: backup code works when TOTP device is unavailable

Disable TOTP: requires current code, removes requirement from future logins

E2E test passes end-to-end in CI

npm run preflight passes clean

Session Notes — Sprint PL.3 This is the security capstone. TOTP was removed in Phase 0 because it was tangled with engineering work that needed a clean surface. Now the surface is stable and tested. Re-implementing TOTP against a working system is cleaner than trying to maintain it through 17 milestones of refactoring. The compute backend kept its TOTP endpoints throughout, so the server side should be intact. The website side needs fresh implementation adapted to any dashboard/admin changes made during Phases 1–5. Use git history as a reference but don't blindly restore — the admin page structure may have changed significantly with the usage display work (M-2B). The E2E test is essential: TOTP touches the most security-critical code path (authentication), so it needs automated verification, not just manual testing.

Expected Outcome: TOTP 2FA fully operational. Sensitive actions gated behind re-authentication. E2E tested.

# Effort Summary & Timeline

| Phase | Milestones | Est. Sessions | Complexity | Parallel? |
| --- | --- | --- | --- | --- |
| P0: Hotfix | M-0A, M-0B | 1.5 | Low–Medium | Both can run in parallel |
| P1: Foundation | M-1A, M-1B, M-1C, M-1D | 6–10 | High | 1A/1C parallel, 1D depends on 1B |
| P2: Observability | M-2A, M-2B, M-2C | 1.5–2.5 | Medium | Sequential (A→B), C parallel with A |
| P3: Email | M-3A, M-3B, M-3C | 2–2.5 | Medium | Sequential (A→B→C) |
| P4: CI/CD | M-4A, M-4B, M-4C | 1.5–2.5 | Medium | All parallel with other phases |
| P5: Hardening | M-5A–M-5D | 4–6 | High | E2E per-tier blocked on P2+P3+P1D |
| Pre-Launch | PL-1, PL-2, PL-3 | 3–4.5 | Medium | After all engineering complete |
| TOTAL | 17 milestones + 3 pre-launch | 18.5–28 |  |  |

Optimal Execution Order Start with Phase 0 (capacity bug fix) — quick win. Then Phase 1A (MMPM /stats) and Phase 4A/4B (CI/CD) in the same session if possible — they have no dependencies on each other and represent the two longest lead-time items. Phase 1B (dedicated chain) and 1C (onboarding tier) can begin in parallel. Phase 3 can start whenever you want email to work. Phase 5 is the final engineering gate. Once all engineering is complete, the Pre-Launch checklist (Stripe go-live + Google indexation) takes the product from test to revenue.

# Technical Reference

## Technology Stack

| Layer | Technology | Version | Purpose |
| --- | --- | --- | --- |
| Frontend | Next.js (App Router) | 15.2.0 | Storefront, dashboard, proxy layer |
| Frontend | React | 19 | UI components |
| Frontend | Tailwind CSS | 4 | Styling |
| Frontend | React Three Fiber | latest | 3D knowledge graph visualization |
| Frontend | Zustand | latest | Client state management |
| Backend | Express | 5.2.1 | API server, webhook handlers |
| Backend | TypeScript | 5.7 | Type safety across both repos |
| Backend | PM2 | latest | Process management (14 workers) |
| Database | PostgreSQL | 16+ | Persistent storage (25 tables) |
| Database | pgBouncer | latest | Connection pooling |
| Database | node-pg-migrate | 8.0.4 | Schema migrations (60+) |
| Payments | Stripe | 20.4.1 | Subscriptions, webhooks, metered billing |
| Email | Resend | 6.9.4 | Transactional email delivery |
| Auth | otplib | 12.0.1 | TOTP 2FA |
| Auth | argon2 | 0.43.0 | Password hashing |
| Infra | DigitalOcean API | v2 | Droplet provisioning |
| Infra | Docker Compose | latest | Substrate containers |
| Infra | Traefik | latest | SSL/TLS gateway, auto-cert |
| Infra | Nginx | latest | Reverse proxy, per-substrate bearer auth |
| Testing | Vitest | 4.1.0 | Unit + integration tests |
| Testing | Playwright | 1.50.0 | E2E browser tests |
| Testing | Testcontainers | 11.13.0 | Dockerized test PostgreSQL |

## Environment Variables Reference

| Variable | Repo | Required | Description |
| --- | --- | --- | --- |
| STRIPE_SECRET_KEY | Compute | Yes | Stripe API key (sk_live_ or sk_test_) |
| STRIPE_WEBHOOK_SECRET | Compute | Yes | Stripe webhook signing secret |
| STRIPE_PUBLISHABLE_KEY | Website | Yes | Stripe public key (pk_live_ or pk_test_) |
| STRIPE_PRICE_*_MONTHLY | Compute | Yes | Stripe price IDs per tier (4 vars) |
| STRIPE_PRODUCT_* | Compute | Yes | Stripe product IDs per tier (4 vars) |
| STRIPE_METER_ATOM_OVERAGE | Compute | Yes | Stripe Billing Meter ID (mtr_test_61UO...) |
| DATABASE_URL | Compute | Yes | pgBouncer connection string |
| DATABASE_URL_DIRECT | Compute | Yes | Direct PG connection (migrations) |
| RESEND_API_KEY | Both | Yes | Resend email API key |
| MMPM_API_URL | Website | Yes | MMPM server URL (https://mmpm.co.nz) |
| MMPM_API_KEY | Both | Yes | MMPM master API key |
| MMPM_VIZ_API_KEY | Website | Yes | MMPM read-only key (public-safe) |
| MMPM_COMPUTE_URL | Website | Yes | Compute backend URL (https://memory.kiwi) |
| DO_API_TOKEN | Compute | Yes | DigitalOcean API token (provisioner only) |
| DO_SSH_KEY_FINGERPRINT | Compute | Yes | SSH key fingerprint for droplets |
| TOTP_ENCRYPTION_KEY | Compute | Yes | AES-256-GCM key (openssl rand -base64 32) |
| INTERNAL_SERVICE_KEY | Both | Yes | Shared secret for internal API calls |
| TRAEFIK_API_TOKEN | Compute | Yes | Bearer token for Traefik /register |
| BASE_URL | Compute | Yes | Magic link base URL |
| GITHUB_WEBHOOK_SECRET | Website | Yes | HMAC-SHA256 webhook signing |
| CONTACT_EMAIL | Website | Yes | Notification recipient email |
| EMAIL_ENABLED | Website | New | Kill switch for email sends (default: true) |

## PM2 Process Map

| # | Process Name | Purpose | Sensitive Tokens |
| --- | --- | --- | --- |
| 1 | compute-server | Express API (port 3100) | STRIPE, DATABASE, TOTP |
| 2 | compute-provisioner | DO droplet creation | DO_API_TOKEN |
| 3 | compute-traefik | SSL cert registration | TRAEFIK_API_TOKEN |
| 4 | compute-destroyer | Droplet snapshot + delete | DO_API_TOKEN |
| 5 | compute-reaper | Queue cleanup (5-min cycle) | DATABASE |
| 6 | substrate-provisioner | Container provisioning | SSH keys |
| 7 | substrate-destroyer | Container teardown | SSH keys |
| 8 | substrate-metering | Daily usage billing | STRIPE Meter |
| 9 | grace-period-worker | Read-only → deprovisioned | DATABASE |
| 10 | tier-change-worker | Tier upgrades/downgrades | SSH keys, DO_API_TOKEN |
| 11 | capacity-worker | Host utilization monitoring | DO_READ_TOKEN |
| 12 | substrate-telemetry | Docker stats + DO metrics | SSH keys, DO_READ_TOKEN |
| 13 | key-rotation-worker | 7-state key rotation SM | SSH keys |
| 14 | ops-inference | Account health analytics | OPS_SUBSTRATE_URL |
| 15 | dedicated-provisioner (NEW) | Droplet → Substrate chain | DO_API_TOKEN, SSH |

## Database Schema Map (25 Tables)

| Table | Purpose | Key Relationships |
| --- | --- | --- |
| accounts | Customer accounts + balance | FK: stripe_customer_id |
| account_credentials | Password hashes (SaaS signup) | FK: account_id |
| auth_sessions | HTTP sessions (30-day TTL) | FK: account_id |
| magic_link_tokens | 15-min single-use tokens | FK: email → accounts |
| sudo_sessions | Sudo challenge tokens (10-min) | FK: account_id |
| instances | Legacy droplet tracking | FK: account_id, droplet_id |
| substrates | SaaS container instances | FK: account_id, host_id |
| substrate_subscriptions | Stripe subscriptions | FK: account_id, stripe_subscription_id |
| compute_hosts | Shared/dedicated hosts | FK from substrates |
| entitlements | Stripe payment → instance | FK: account_id, instance_id |
| billing_events | All financial transactions | FK: account_id, entitlement_id |
| spend_caps | Customer spend limits | FK: account_id |
| api_keys | Account API keys | FK: account_id |
| usage_ledger | Per-minute usage tracking | FK: instance_id |
| provision_queue | Legacy droplet queue | FK: account_id, instance_id |
| substrate_provision_queue | Container provisioning queue | FK: substrate_id |
| destroy_queue | Droplet destruction queue | FK: instance_id |
| substrate_tier_changes | Tier change jobs | FK: substrate_id |
| traefik_config_queue | SSL cert outbox | FK: instance_id |
| key_rotation_jobs | 7-state rotation SM | FK: api_key_id |
| platform_settings | Global settings singleton | None (singleton row) |
| capacity_waitlist | Signup capacity gating | FK: account_id |
| host_telemetry_snapshots | Docker/DO metrics cache | FK: host_id |
| substrate_port_pool | Host port allocation | FK: substrate_id, host_id |

# Launch Acceptance Criteria

The following criteria must all be met before the product is considered feature-complete and ready for public launch. Each criterion maps back to a specific milestone.

| Criterion | Definition of Done | Milestone |
| --- | --- | --- |
| Capacity Endpoint Working | GET /api/capacity returns valid JSON with tier availability. Pricing page renders badges correctly. | M-0A |
| TOTP + Sudo Removed | No TOTP or sudo code remains in website during engineering. Login is magic-link only. | M-0B |
| TOTP Re-implemented | TOTP 2FA fully operational pre-launch. Sensitive actions gated behind TOTP re-authentication. E2E tested. | PL-3 |
| Accurate Usage Display | Dashboard shows real-time atom count, bootstrap usage, and storage for every active substrate. No zeroes unless the substrate is genuinely empty. | M-2B |
| Billing Integrity | Stripe charges accurate overages based on real usage data. Billing status endpoint returns correct subscription state, usage, and limits. | M-2A, M-2C |
| Dedicated Hosting | A customer can check out the Team tier and receive a dedicated droplet with a running substrate within 5 minutes, fully automated. | M-1B |
| Lossless Tier Migration | A customer upgrading or downgrading between tiers retains ALL atoms and edges. Zero data loss on tier change. | M-1D |
| Onboarding Tier Live | New users can sign up for the onboarding tier and experience genuine value before upgrading. | M-1C |
| Lifecycle Emails | Customers receive welcome, payment confirmed, payment failed, grace period, and cancellation emails at the correct lifecycle moments. | M-3A, M-3B |
| Automated Deployment | Both repos deploy automatically on push to main via GitHub Actions. Migrations run before code restart. Health checks confirm success. | M-4A, M-4B |
| Rate Protection | Nginx rate limits are active on auth and API endpoints, preventing abuse while allowing legitimate traffic. | M-5A |
| Per-Tier E2E Validated | Playwright tests exercise the full customer journey for every product tier, including tier upgrades with data preservation. | M-5B |
| Developer Onboarding | A developer can visit /developers, read the quickstart, configure Claude Desktop, and make their first memory call without external help. | M-5C |
| Stripe Live Mode | All Stripe products, prices, and the billing meter are in live mode. Real payments can be processed. No test-mode artifacts remain active. | PL-1 |
| Google Indexed | Site appears in Google search results. FAQPage JSON-LD renders in rich results. No crawl errors. | PL-2 |

Parametric Memory — Milestones Program v2.0 (Evidence-Based)

Generated April 09, 2026 — Architecture Review Session

Evidence: Stripe MCP, Ops MCP, live endpoints, code review